## Sheet1
Experience Based Co-design - project generic timeline (simplified version)
Month Number | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Set-Up Phase
Discernment exercise - identifies transition of focus.
Agree membership of steering group (Core plus intensive)
Agree membership of working group (intensive)
EBCD Training
Kick off meeting- identify teams, sign up staff for listserve, bookmark POC toolkit, get filming equipment together, schedule regular meetings, organise meeting rooms for events, budget for events / parent support. Consider/start VON charter with scope of work, milestones etc to be updated during year
Determine and secure IRB and other approvals
High level Process map
Discovery Phase
Observations of care / shadowing
Initial high level key driver diagram to be updated during year
Staff interviews (approx 5)
Identify and recruit families for interview
Family interviews (approx 5)
Continue staff and family interviews (x8)
Analysis phase
Analysis of staff and patient interview and observation data
Staff feedback event
Edit film / other interview and shadowing data
Patients view and approve films / other media
Re-edit film and add introduction if required
Family feedback event
Joint patient and staff event
Co-design priorities identified and co-design groups formed
Co-design phase
Co-design phase: Smart Aims
Co-design phase: Measurement Plans
Co-design phase: Complete draft charter
Co-design phase: KDD
Co-design phase: Test change ideas (PDSA cycles)
Co-design phase Measure process and outcomes
Assessment Phase
Collate outputs from co-design groups
Begin planning for Year 2
Report Out to Leadership
Celebration event
Set-Up Phase
Discovery Phase
Analysis phase
Co-design phase
Assessment Phase