## Sheet1
Experience Based Co-design - project timeline (full version) | week commencing
Weekly Monday Dates | time axis 2019-01-07 to 2019-12-09
Intensive webinars / quality congress
Core webinars
Key activities | 2019-01-07: 2019-01-01; 2019-02-04: 2019-02-01; 2019-03-04: 2019-03-01; 2019-04-01: 2019-04-01; 2019-04-29: 2019-05-01; 2019-06-03: 2019-06-01; 2019-07-01: 2019-07-01; 2019-08-05: 2019-08-01; 2019-09-02: 2019-09-01; 2019-10-07: 2019-10-01; 2019-11-04: 2019-11-01; 2019-12-02: 2019-12-19
Prelaunch webinar-intensive | bar: 2019-01-07
Set-Up Phase | bar: 2019-01-07 to 2019-02-18
Discernment exercise - identifies transition of focus. | bar: 2019-01-07 to 2019-01-28
Agree membership of steering group (Core plus intensive) | bar: 2019-01-14 to 2019-01-28
Agree membership of working group (intensive) | bar: 2019-01-14 to 2019-01-28
EBCD Training | bar: 2019-01-14 to 2019-02-18
Kick off meeting- identify teams, sign up staff for listserve, bookmark POC toolkit, get filming equipment together, schedule regular meetings, organise meeting rooms for events, budget for events / parent support. Consider/start VON charter with scope of work, milestones etc to be updated during year | bar: 2019-01-14 to 2019-02-18
Determine and secure IRB and other approvals | bar: 2019-01-14 to 2019-02-18
VON DAY AUDIT 1 | bar: 2019-02-11 to 2019-02-18
High level Process map | bar: 2019-02-11 to 2019-02-18
Webinar A | bar: 2019-02-25
Discovery Phase | bar: 2019-02-18 to 2019-05-06
Observations of care / shadowing | bar: 2019-03-04 to 2019-03-25
Initial high level key driver diagram to be updated during year | bar: 2019-03-04 to 2019-04-01
Staff interviews (approx 5) | bar: 2019-03-18 to 2019-04-08
Identify and recruit families for interview | bar: 2019-03-25 to 2019-04-15
Family interviews (approx 5) | bar: 2019-04-08 to 2019-04-29
Webinar B | bar: 2019-04-29
Continue staff and family interviews (x8) | bar: 2019-04-29 to 2019-05-27
Analysis phase | bar: 2019-05-06 to 2019-07-29
Analysis of staff and patient interview and observation data | bar: 2019-05-06 to 2019-05-27
Staff feedback event | bar: 2019-06-03
Edit film / other interview and shadowing data | bar: 2019-06-03 to 2019-06-24
Patients view and approve films / other media | bar: 2019-07-01
Re-edit film and add introduction if required | bar: 2019-07-08 to 2019-07-15
Family feedback event | bar: 2019-07-22
Joint patient and staff event | bar: 2019-07-22 to 2019-07-29
Co-design priorities identified and co-design groups formed | bar: 2019-07-29
Submit Abstract and / or video for AQC | bar: 2019-07-01
Faculty feedback on abstracts | bar: 2019-08-05 to 2019-08-12
Co-design phase | bar: 2019-07-29 to 2019-11-18
Co-design phase: Smart Aims | bar: 2019-08-05 to 2019-08-24
Co-design phase: Measurement Plans | bar: 2019-08-05 to 2019-09-02
Co-design phase: Complete draft charter | bar: 2019-08-05 to 2019-09-02
Co-design phase: KDD | bar: 2019-08-05 to 2019-09-02
Co-design phase: Test change ideas (PDSA cycles) | bar: 2019-08-05 to 2019-11-18
Co-design phase Measure process and outcomes | bar: 2019-08-05 to 2019-11-18
Annual Quality Congress | bar: 2019-10-07
Assessment Phase | bar: 2019-10-28 to 2019-12-09
VON DAY AUDIT 2 | bar: 2019-10-28 to 2019-11-04
Collate outputs from co-design groups | bar: 2019-10-28 to 2019-11-18
Webinar C | bar: 2019-11-11
Begin planning for Year 2 | bar: 2019-11-11 to 2019-12-09
Report Out to Leadership | bar: 2019-11-11 to 2019-12-09
Celebration event | bar: 2019-11-25 to 2019-12-09
Set-Up Phase | bar: 2019-01-07 to 2019-02-18
Discovery Phase | bar: 2019-02-18 to 2019-04-29
Analysis phase | bar: 2019-04-29 to 2019-07-29
Co-design phase | bar: 2019-07-29 to 2019-10-28
Assessment Phase | bar: 2019-10-28 to 2019-12-09